Mad River Local Schools District OIP School Improvement Plan with Implementation Details

| Smart Goals |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Graduation |  |  |  |  |  |
| Goal 2: By May 2021, 90% of Mad River Local Schools students will graduate on time with their cohort group |  |  |  |  |  |
| Strategies, Indicators and Progress Measures |  |  |  |  |  |
| ### Strategy 1a: Implement district-wide systematic practices to ensure on-time graduation |  |  |  |  |  |
|  | Baseline Measure (Date) | Progress Measure (Date) | Progress Measure (Date) | Progress Measure (Date) | Progress Measure (Date) |
| ### Adult Implementation Indicator (s) Each building will increase their percentage of Tier I implementation (teams, implementation, and evaluation of implemented programs) as measured by the annual Tiered Fidelity Inventory (TFI). | 2017-2018 TFI Results: - VS- Teams (100%), Implementation (72%), Evaluation (100%) | June 2019 VS - VS- Teams (75%), Implementation (72%), Evaluation (88%) |  |  |  |
| ### Student Performance Indicator (s) - At VS 100% of students will meet expectations to earn the monthly/quarterly PBIS reward. | - For the 2016-2017 school year, the four elementary buildings averaged 90% of students meeting the expectations to participate in their given rewards (monthly/quarterly). VS: 91.6% | June 2019 VS - VS- 92% |  |  |  |

Implementation Details

| Action Steps | Monitoring Evidence/Data Sources | Person(s) Responsible/ Group(s) | Implementation Timeline |  |  |  |  |  |  |  |  |  |  |  | Resources Needed/Tasks: Budget/Material/ Technology/Etc. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | July |  |
| 1.a.4 Each Building will create an action plan for two areas of foci as a result of the annual TFI. | Completed TFI Report | SST Region 10 Consultants Each building (Pre-K thru SHS) & Transportation |  |  |  |  |  |  |  | X | X | X |  |  |  |
| 1.a.5 The DLT Subcommittee will review specific building data (in order to determine needs) four times a year. | K-4 (Monitoring Sheet-TBDesigned) | Each building’s PBIS Committee, DLT PBIS Subcommittee |  |  | X |  | X |  |  | X |  |  | X |  |  |
| 1.a.6. Investigate and provide differentiated support (PD) based on building need(s) as evidenced by yearly TFI results, district progress measuring tool (2-3x/year) | TFI results/plan, Specific PD based on category of referrals, PSW Data, district progress measuring tool (2-3x/year) | Supervisor of Student Services/Curriculum Support, Bldg Admin, DLT PBIS Subcommittee, Building PBIS Team, Therapist, | X | X | X | X | X | X | X | X | X | X | X |  | PBIS PD based on TFI needs analysis: Eric Jensen Poverty Awareness/Social/Emotional PD, ACES PD, Trauma PD |