OIP School Improvement Plan with Implementation Details

| Smart Goals |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Instruction |  |  |  |  |  |
| Goal 1: By 2021 students will improve reading proficiency by 15% as measured by district and state assessments. |  |  |  |  |  |
| Strategies, Indicators and Progress Measures |  |  |  |  |  |
| ### Strategy 1a: Improving literacy instructional experiences for students and teachers through study, dialogue and experimentation. |  |  |  |  |  |
|  | Baseline Measure (Date) | Progress Measure (Date) | Progress Measure (Date) | Progress Measure (Date) | Progress Measure (Date) |
| ### Adult Performance Indicator (s) Involvement in literacy professional development as measured by participation in waiver days, presentations, BLT monthly discussions “Learning through Implementation”. | By May 2017, the district will collect baseline data Baseline: 1/24 By May of 2018: 4/24 | By June 2019 20/24 | By June 2020 | By May 2021 |  |
| ### Adult Implementation Indicator (s) Implementation of a systematic understanding of literacy in all content areas as measured by participation in reflective practitioner discussions through waiver days, TBT PD sessions, BLT meetings. | By May of 2018: Administration: 0/1 Teaching Staff: Baseline: 0/24 | By June 2019 Administration: 0/1 Teaching Staff: Baseline: 5/24 | By June 2020 | By May 2021 |  |
| ### Student Performance Indicator (s) Portfolios: - Focusing Task Questions - End of Module Tasks - Informative and Narrative Writing - STAR/NWEA-MAP - AIR | By May 2018, the district will collect baseline data 4/24 | By June 2019 20/24 | By June 2020 | By May 2021 |  |

Implementation Details

See attached documents for implementation details of the 3 Year Plan

| Action Steps | Monitoring Evidence/Data Sources | Person(s) Responsible/ Group(s) | Implementation Timeline |  |  |  |  |  |  |  |  |  |  |  | Resources Needed/Tasks: Budget/Material/ Technology/Etc. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | July |  |
| 1.a.1 Define literacy and roll out of instructional goal | District roll-out presentation and handouts | Curriculum |  |  |  |  |  |  |  |  | X | X | X |  | Literacy Plan Year 1 |
| 1.a.2 Schedules and restructuring time for lit | Building schedules, literacy instruction expectations | Administration | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-3 |
| 1.a.3 On-going literacy PD on waiver days and Summer PD sessions | District-wide PD Plan, reflections, assignments | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-3 |
| 1.a.4.Develop and deliver literacy PD to district and building admin | Agendas, reflections | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 2-3 |
| 1.a.5 Schedule and implement Instructional coach model lessons and video guild project | Coach schedules, reflections | Curriculum |  |  |  |  |  |  |  |  |  |  |  |  | Literacy Plan Year 1-3 |
| 1.a.6.Development of TBT PD sessions based on needs analysis and teacher reflections | Focusing Arc Planning Tool, agendas | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-2 |
| 1.a.7 Sub training, support staff training | Schedule for New Sub Training, Agenda | HR & Curriculum |  |  | X | X |  |  |  |  |  |  |  |  | Literacy Plan Year 1-3 |
| 1.a.8. Analyze data from Focusing Question Tasks, End of Module Assessments, and AIR | Data Analysis, writing samples | Curriculum & Administration | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1 |
| 1.a.9. Consistently plan and attend BLT meetings | Schedule, Agendas, Artifacts | Principals and Coaches | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-3 |
| 1.a.10.Develop and implement PD to strengthen understanding of literacy K-12 | PD artifacts, literacy plan | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-3 |
| 1.a.11 Implement parent communication and engagement plan | Flyers, Schedule, feedback, surveys | Administration and Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 2 |
| 1.a.12 Develop PD plan for Literacy in content areas | PD plan, needs analysis | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 2 |
| 1.a.13Research sub groups effect of core curriculum | Assessment Results, student artifacts and data | Curriculum and Administration | X | X | X | X |  |  |  |  |  |  | X | X | Literacy Plan Year 2-3 |
| 1.a.14 Collection of reflections from staff | Exit slips from PD, discussions, socratic seminars, 365 reflections | Curriculum | X | X | X | X | X | X | X | X | X | X | X |  | Literacy Plan Year 1-3 |

| 1.a.15 Each staff member will visit a peer to observe a WW lesson | Schedule, reflection prompts, template for discussion | BLT and TBT’s with coaches support | X | X | X | X | X | X | X | X | X | X | X |  |  |  | Literacy Plan Year 2-3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |